## Slide 1
Azure to AWS
Cloud Migration Programme
Executive Briefing · Enterprise Architecture · June 2026
Strategic Platform Unification
50TB Data Estate Migration
Serverless ETL Modernisation
Notes: Opening slide. Introduce the programme: mandatory Azure exit with a hard contract deadline. The three pillars frame the strategic scope.

## Slide 2
Why This Migration — and Why Now
MANDATORY EXIT
Azure contract has a hard end date within the next 6–9 months.
This is not a cost-optimisation exercise. It is a contractual obligation.
Failure to complete by the deadline results in emergency renewal or crash-programme delivery — both significantly more expensive than planned execution.
STRATEGIC OPPORTUNITY
→ Single cloud vendor across the entire organisation
→ Native data sharing with wireless business unit on AWS
→ Unified security model: one IAM, one audit trail, one compliance framework
→ Open-source portable ETL — no proprietary ETL vendor lock-in
→ AWS telco capabilities now accessible to both business units
STRATEGIC CONTEXT
Notes: Two points: (1) this migration is mandatory — not a choice; and (2) completing it unlocks strategic value that dual-cloud cannot provide. Focus the Board on the cost of inaction as much as the cost of action.

## Slide 3
Migration Scope
CURRENT STATE — Azure
Azure SQL Managed Instance
50TB estate · 2TB OLTP
Azure Data Factory
Pipeline orchestration + Data Flows
SSIS on Azure VM
Complex ETL packages
Windows Services on Azure VM
Scheduled + polling batch workers
Azure Functions (in ADF)
Event-driven compute
SFTP/MFT on Azure VM
Partner file exchange
→
TARGET STATE — AWS
AWS RDS for SQL Server
Multi-AZ · Same engine, lift-and-shift · Native backup/restore
AWS Glue + Step Functions
PySpark ETL + orchestration
Glue PySpark Jobs
SSIS rewrite — open Apache Spark
EventBridge + Lambda + Glue
Serverless · zero VM dependency
AWS Lambda
Replaces Azure Functions
AWS Transfer Family
Managed SFTP · S3 event-driven
MIGRATION SCOPE
Notes: What is moving: every component of the Azure estate. Emphasise that the Azure VM (running SSIS and Windows Services) is eliminated entirely — not migrated but replaced by serverless compute.

## Slide 4
Target Architecture
INGESTION
AWS DMS (CDC)
EventBridge
Transfer Family (SFTP)
GitHub Actions CI/CD
PROCESSING
Glue PySpark Jobs
Glue Visual ETL
Step Functions
AWS Lambda
STORAGE
RDS for SQL Server
S3 + Parquet (T2/T3)
Athena (cold archive)
Glue Data Catalog
CONSUMERS
Applications (SqlClient)
BI / Reporting
DW Subscribers
CloudWatch Ops
↓
↓
↓
TARGET ARCHITECTURE
Notes: Walk through the four layers: Ingestion (how data gets in), Processing (how it is transformed), Storage (where it lives in tiers), Consumers (who uses it). The key message: zero VMs in the target state — everything is managed or serverless.

## Slide 5
Programme Timeline — 28 Weeks
Schema & DB Code
AWS SCT + GHCP
App DB (DMS CDC)
Full Load → CDC → Cutover
Replication Retirement
Subscriber replacement
SSIS → PySpark
Starts Week 1 — critical path
ADF → Glue ETL
GHCP + custom tool
App Remediation
Connection strings · pool tuning
Testing & UAT
Gate criteria → UAT → Cutover
Wk4
Wk12
Wk20
Wk26
Wk28
◆ Wk4 Go/No-Go
◆ CUTOVER
PROGRAMME TIMELINE
Notes: Seven parallel workstreams. The critical path is the SSIS rewrite stream — starts Week 1, runs 20 weeks. The Week-4 Go/No-Go gate is where census results confirm the timeline is achievable. Cutover target is Week 26.

## Slide 6
Programme Gates & Key Decisions
Wk 1
Estate Census Begins
Five DB censuses + full ETL inventory: SSIS, Windows Services, Azure Functions, SFTP partners. Object counts drive every timeline commitment.
Wk 3
Architecture Decisions (G1 gate)
Linked server redesign, collation strategy, MSDTC disposition, CLR objects — all architect decisions signed off. No batch conversion before G1.
Wk 4
Go / No-Go Gate
Business Sponsor in the room. Real census data. If SSIS count or SP complexity exceeds plan: re-baseline the timeline now, not in Phase 3.
Wk 6
DMS CDC Starts (DDL Freeze)
Database migration begins. DDL freeze active from this point — no schema changes for ~20 weeks. Communicated to all teams in Week 5.
Wk 24
13 Cutover Gate Criteria
CDC lag <2s for 72h, all ETL parallel runs clean, application regression green, SFTP partners switched, performance baseline met. All 13 must be green.
Wk 26
Cutover Weekend
14-step runbook. T+4hr Go/No-Go decision. Pre-built rollback automation available. Azure remains live read-only for 4 weeks as safety net.
PROGRAMME GOVERNANCE
Notes: Six gates that matter to the Board. The Week-4 gate is when the Sponsor must be in the room — that is the last decision point where a re-baseline (adding weeks) is commercially manageable. After Week 8, delay becomes expensive.

## Slide 7
Top Programme Risks
Critical
Undocumented Business Logic
SSIS packages encode business rules that exist nowhere else. Faithful migration migrates bugs. Mitigation: business SME reviews requirements documents before code generation.
Critical
Rollback Data Loss After Cutover
Writes to RDS SQL Server after cutover are not recoverable if the technical rollback is executed. Mitigation: business formally agrees an acceptable data loss window before cutover day.
High
BAU Conflict Reduces Team Capacity
28 weeks of parallel workstreams requires fully dedicated team members. BAU coverage for each dedicated role must be arranged before Week 1.
High
SSIS Rewrite Scope Underestimated
SSIS has no automated port to AWS Glue. Week-1 census provides exact package count. Timeline re-baselined at Week-4 gate if needed.
High
RDS Feature-Parity Gap Discovered Late
Service Broker, FileStream, and MSDTC are not supported on RDS SQL Server. Full feature-parity audit in Week 1-2 surfaces any gap before it becomes a cutover blocker.
High
SFTP Partner Coordination Delay
External partners need 4–12 weeks notice to switch SFTP endpoints. Outreach must begin Day 1. Cutover cannot proceed until all partners confirm.
RISK SUMMARY
Notes: Six risks that the Board should be aware of. The first one (undocumented business logic) is the only risk that has no technical mitigation — it requires business SME engagement. The others all have defined mitigation plans in the programme.

## Slide 8
Programme Team & Governance
Part-time
Programme Sponsor
Board gate decisions · Budget authority · Stakeholder management
Dedicated
Migration Lead
Cross-stream coordination · Risk escalation · Weekly heartbeat
Dedicated
DBA Lead + Team
Infrastructure migration · DMS CDC · Performance tuning
Dedicated
ETL Lead + Team
SSIS/ADF/Windows Svc/Azure Fn migration · Custom tool
Dedicated
Application Lead + Team
Data access audit · Connection updates · Feature-parity checks
Dedicated
Cloud Architect
AWS environment design · RDS/Glue/Lambda/SFN · Security
Existing team
RDS SQL Server Specialist
G1 gate decisions · Feature-parity audit · Cutover support
Part-time
Business SMEs
Requirements doc review · Business outcome tests · UAT sign-off
TEAM STRUCTURE
Notes: Key message: dedicated roles must have BAU coverage arranged before Week 1. With the database target now RDS SQL Server (same engine as source), the existing DBA team's skills transfer directly — no external database specialist engagement is required, unlike the originally-planned PostgreSQL migration.

## Slide 9
Cutover Design & Rollback Safety
14-Step Cutover Runbook — Target Wk 26
T-0
Stop user writes
T+10
Verify quiesced
T+15
CDC lag = 0
T+25
Stop DMS
T+30
Switch to RDS
T+37
Activate Lambda
T+55
Resume writes
T+4hrs
Go/No-Go
ROLLBACK DESIGN
• Pre-built GitHub Actions rollback: <5 minutes
• Reverts connection strings to source automatically
• Source remains live read-only for 4 weeks post-cutover
• Data written to RDS SQL Server after cutover is NOT recoverable on rollback
• Acceptable data loss window agreed with business BEFORE cutover day
13 CUTOVER GATE CRITERIA
✓ DMS CDC lag <2s for 72 consecutive hours
✓ All ETL parallel runs: 0 discrepancies
✓ RDS SQL Server p95 within 15% of baseline
✓ Application regression: 0 critical failures
✓ Case-sensitivity regression: exact match
✓ All SFTP partners switched and confirmed
✓ Rollback rehearsed in staging (<5 min)
CUTOVER & ROLLBACK
Notes: The rollback data loss caveat is critical: any writes to RDS SQL Server after cutover are not recoverable on rollback. The business must formally agree an acceptable data loss window and a data recovery procedure before cutover day. This is not a technical decision — it is a business risk acceptance decision.

## Slide 10
What We Need from the Board
1
Approve the migration programme for immediate execution
The Azure contract clock is running. Delay costs more than it saves.
2
Approve the programme budget and team capacity plan
Dedicated roles require BAU coverage. Investment recovers within 12–14 months of Azure exit.
3
Confirm RDS SQL Server licensing decision
License Included vs BYOL — required before the G1 architecture gate (Week 3). Drives the AWS steady-state cost figure.
4
Confirm business SME availability for requirements review
SMEs must review ETL requirements documents before code generation. UAT sign-off is not sufficient.
5
Pre-agree the rollback data loss window before cutover day
Business must formally accept the data recovery procedure. This is a Board-level risk acceptance.
Notes: This is the decision slide. Five things the Board must decide today or in the next 48 hours. None of these are technical decisions — they are all programme governance and risk acceptance decisions that only the Board or Sponsor can make.

## Slide 11
Supporting Documentation
~37p
Migration Plan v6.0
Master programme plan: all workstreams, phases, 24-risk register, programme governance, 30-day action plan, 14-step cutover runbook. Updated for RDS SQL Server target.
~16p
RDS SQL Server Infrastructure Guide
Platform design for the lift-and-shift target: licensing decision, instance sizing, feature-parity audit, homogeneous DMS migration, security, Day 2 operations. Replaces the archived Schema Conversion Guide.
~51p
ETL Migration Guide v4.0
ADF, SSIS, Windows Services, Azure Functions, SFTP/MFT, ordering patterns, custom tool, testing strategy, ETL governance, Day 2 operations
~34p
Custom Tool Implementation v2.0
Custom migration tool: requirements doc schema, five-layer hybrid code generation, three-phase pattern rules, Sprint 0 build plan. Updated for pyodbc/T-SQL target.
~21p
Business Case v2.0
Mandatory Azure exit, cost of inaction, investment required, financial return, risk assessment. Updated for RDS SQL Server cost model.
~14p
Enterprise Architect Review
Independent assessment: scorecard across 11 dimensions, structural corrections made, what is strong vs what needed correction
Notes: Reference slide for the full document suite. All documents are enterprise-ready and have been corrected based on the EA independent review. The EA review scorecard and correction log are in the EA Independent Review document.